## Sheet1
Component | Priority | Estimated Time | Actual Time
Layout and Structure (Welcome Page) | High | 2 hours | 3 hours
Layout and Structure (Game Page) | High | 2 hours | 3 hours
Put together JSON data page(English:Esperanto) | High | 3 hours | 1 hour
Coding logic to pull up random English words | High | 3 hours | 8 hours
Coding logic to match the player's words to the corresponding Esperanto words | High | 3 hours | 4 hours
Coding logic to count the player's score | High | 3 hours | 4 hours
Adding a timer and coding logic that wouldn't allow the player to move to a new group of words until they get at least 8 out of 10 correct | Medium | 3 hours | not done yet
Making the game playable on phones and tablets | Medium | 3 hours | not done yet
Coding logic to make sure that the buttons and return key worked properly | HIgh | not estimated | 5 hours
Making the game more attractive to look at | High | not estimated | 4 hours
Total Estimated Time |  | 22 hours | 33 hours